## Sheet1
Assignment #3
Assignee Name | Email | Task | Duration (hours) | Dependency | Due Date | Note
Ivana Lanzani | ilanzani1@student.gsu.edu | Parallel Computing Question/Answers | 2 hours | All Previous task completed | 2019-10-23 | Task done on time
Meet Patel | mpatel165@student.gsu.edu | Assignment Report | 3 hours | None | 2019-10-24 | Complete it 24 hrs before due date/Task done on time
Dominick DiLeo | ddileo2@student.gsu.edu | Parallel Programming | 3 hours | None | 2019-10-22 | Task done on time
Akiva Ochoa | aochoa5@student.gsu.edu | Arm Assembly Programming | 2 hours | All Previous task completed | 2019-10-22 | Task done on time
Chowdhury Mobin (Coordinator) | cmobin1@student.gsu.edu | Planning & Scheduling Tasks,Slack,Github,Video | 2 hours | Video Recording/Editing | 2019-10-24 | Final editing must be done 24 hrs. before due date/Task done on time