## Sheet1
Assignment #2
Asignee Name | Email | Task | Duration (hours) | Dependency | Due Date | Note
Ivana Lanzani | ilanzani1@student.gsu.edu | Parallel Programming Basics and recording video | 3 hours | All Previous task completed | 2019-10-01 | Video editing ready before 24 hrs/Task done on time
Meet Patel | mpatel165@student.gsu.edu | Planning and scheduling of task | 2 hours | Video Recording | 2019-10-03 | Task done on time
Dominick DiLeo | ddileo2@student.gsu.edu | ARM Assembly Programming | 2 hours | None | 2019-10-01 | Task done on time
Akiva Ochoa | aochoa5@student.gsu.edu | Assignment Report | 3 hours | All Previous task completed | 2019-10-03 | Report ready before 24 hrs/ Task done on time
Chowdhury Mobin | cmobin1@student.gsu.edu | Raspberry PI Question/Answers | 1 hours | Video Recording | 2019-10-01 | Task done on time